## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a Quality Auditor, I want to upload customer support transcripts so that they can be analyzed by AI. | MUST HAVE | None | FATHIMATH RASHA | 3- Completed
Sprint 1 | Sprint 1 | US02 | As an Auditor, I want the AI to score transcripts for empathy, resolution, and compliance. | MUST HAVE | US01 | FATHIMATH RASHA | 3- Completed
Sprint 1 | Sprint 1 | US03 | As a Supervisor, I want to receive alerts for critical compliance violations in audits. | MUST HAVE | US02 | FATHIMATH RASHA | 3- Completed
Sprint 2 | - | US04 | As a Supervisor, I want to see a leaderboard of agent performance scores. | SHOULD HAVE | US02 | FATHIMATH RASHA | 3- Completed
Sprint 2 | - | US05 | As an Auditor, I want to generate detailed PDF reports of individual audit results. | SHOULD HAVE | US02 | FATHIMATH RASHA | 3- Completed
Sprint 2 | - | US06 | As a Supervisor, I want to export an Excel summary of all recent audits for bulk review. | SHOULD HAVE | US02 | FATHIMATH RASHA | 3- Completed
Sprint 3 | - | US07 | As an Supervisor, I want to manage agent profiles and their metadata (name, email, role). | SHOULD HAVE | None | FATHIMATH RASHA | 3- Completed
Sprint 3 | - | US08 | As a Agent, I want to see a trend analysis graph of quality scores over the last 30 days. | COULD HAVE | US04 | FATHIMATH RASHA | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 60 | 12 | 6 | 10 | 5 | 9 | 4 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Initial implementation of Backend and Frontend structures | 2026-02-25 | 2026-02-25 | Parasuram | Setup | Completed | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Database schema design and script creation (init_db.py) | 2026-02-26 | 2026-02-26 | Rasha | Database | Completed | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T03 | Implementation of AI scoring and transcript management | 2026-02-27 | 2026-02-27 | Saritha | Development | Completed | 12 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US01 | T04 | UI polish and frontend-backend integration | 2026-02-28 | 2026-03-03 | Anjali | Integration | Completed | 10 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T05 | Update README & core documentation | 2026-03-10 | 2026-03-10 | Parasuram | Doc | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T06 | Audit data preparation & env config | 2026-03-15 | 2026-03-20 | Rasha | Setup | Completed | 8 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T07 | Web application deployment | 2026-03-20 | 2026-03-20 | Parasuram | Deploy | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2026-02-25 | None | Successfully initialized the Git repository and local dev environment.
Sprint 1 | 2026-02-26 | SQLite database locking issues during test scripts. | Switched to a more robust connection pooling method in manage_db.py.
Sprint 1 | 2026-02-27 | AI API key rate limits reached during transcript tests. | Implemented exponential backoff and localized testing data.
Sprint 2 | 2026-03-10 | Missing dependency versions in README. | Conducted a full audit of requirements.txt and updated docs.
Sprint 2 | 2026-03-20 | Deployment failure due to environment variable misconfig. | Verified variables in the control panel and redeployed successfully.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-25 | 2026-03-10 | Parasuram | Peer review for AI prompts | Pushing code without local DB tests | Daily 15-min stand-ups | Established prompt review checklist
2 | 1 | 2026-02-25 | 2026-03-10 | Saritha | Weekly quality syncs | Manual CSV formatting | Using GenAI for auto-scoring | Automated the ingestion pipeline
3 | 2 | 2026-03-11 | 2026-03-25 | Parasuram | Automated env-variable audits | Hardcoding sensitive config | Robust error logging | Implemented .env validation scripts
4 | 2 | 2026-03-11 | 2026-03-25 | Rasha | Staging environment tests | Direct production deployments | Using Docker for consistency | Created a staging-to-prod pipeline
5 | 2 | 2026-03-11 | 2026-03-25 | Anjali | Stakeholder feedback loops | Delaying documentation updates | Bi-weekly progress reports | Updated README and help modules
6
7